## Stakeholder_Communication
| Result of analysis |  |  |  |  | Planned management
No. | Stakeholder | Category | Type | Need/requirement | View | Priority | Strategy | Implementation | Due date | Frequency
1 | Employees | D | Internal | Needs: Technical guidance & operational support.Requirements: Fair compensation, clear documentation. | Critic | M | Involve | Provide on-demand technical assistance and operational briefs. | 2026-06-01 | On demand
2 | Customers & Utilities | A | External | Needs: Market demand alignment & product specifications.Requirements: On-time delivery, quality assurance metrics. | Very critic | H | Dialogue | Facilitate structured focus groups and co-design workshops. | 2026-10-01 | Scheduled
3 | Organization Leadership | A | Internal | Needs: Capital funding & resource optimization.Requirements: Successful delivery, comprehensive milestone reporting. | Advocate | H | Manage | Establish a structured daily reporting governance framework. | 2026-06-01 | Daily
4 | Illicit Actors (Drug-Dealers) | C | External | Needs: Maintenance of unmonitored public spaces.Requirements: Interruption of illicit activities near assets. | Very critic | L | Watch | Coordinate site surveillance and design defenses with law enforcement. | 2026-09-28 | Periodically
5 | Federal government | B | External | Needs: Regulatory alignment & strategic grant funding.Requirements: Strict legal compliance, statutory reporting. | Supporter | M | Involve | Submit standardized progress compliance reports. | 2026-09-28 | Periodically
6 | Home owners | D | External | Needs: Minimal service disruption & asset protection.Requirements: Quality assurance, reliable pipeline infrastructure. | Supporter | H | Dialogue | Distribute critical project milestone updates via formal notices. | 2026-09-28 | Periodicallly
7 | Local Residents | D | External | Needs: Uninterrupted utility access & community safety.Requirements: Reassurance of infrastructure durability. | Advocate | H | Dialogue | Broadcast community-level milestone updates at key intervals. | 2026-09-28 | Periodically
8 | Investors | A | Internal | Needs: Financial oversight & risk mitigation.Requirements: Project ROI, transparent progress reports. | Neutral | H | Involve | Conduct formal quarterly investor briefings and financial reviews. | 2026-07-13 | Quarterly
9 | Technical suppliers | D | Internal | Needs: Clear supply chain demands & forecasting.Requirements: Prompt payment terms, streamlined logistics data. | Supporter | H | Involve | Establish an on-demand technical data exchange pipeline. | 2026-07-13 | On demand
10 | Vandals | A | External | Needs: Destruction or theft of public utility components.Requirements: Mitigation of illicit activities near assets. | Very critic | H | Watch | Make the product undisireable to steal and physically hard. | 2026-10-19 | Frequently
11 | The unemployed | C | External | Needs: Economic opportunity & localized socio-economic health.Requirements: Mitigation of public infrastructure deterioration. | Critic | M | Watch | Implement localized public awareness campaigns regarding project benefits. | 2026-10-19 | Periodically
12 | Plumbers | D | Internal | Needs: Practical deployment protocols & expert training.Requirements: Fair compensation, explicit safety/installation manuals. | Critic | M | Involve | Issue targeted operational updates during key deployment phases. | 2026-10-19 | Periodically
13 | Tourists | C | External | Needs: Unobtrusive infrastructure & aesthetic preservation.Requirements: Visually integrated, low-impact design solutions. | Advocate | L | Influence | Deploy public signage and aesthetic/environmental impact notices. | 2026-11-23 | Frequently
14 | Teenagers | D | External | Needs: Constructive community engagement platforms.Requirements: Safe public spaces, alignment with community interests. | Supporter | L | Influence | Release targeted public safety and community awareness campaigns. | 2026-11-23 | Scheduled
15 | Policemen | B | External | Needs: Inter-agency cooperation & site risk profiles.Requirements: Clear security protocols, public safety alignment. | Advocate | H | Inform | Share security logs and project timelines on demand. | 2026-09-28 | On demand
16 | Courts | B | External | Needs: Legal compliance documentation.Requirements: Statutory alignment, transparency. | Supporter | M | Inform | Provide verified compliance portfolios during scheduled reviews. | 2026-09-28 | Periodically
17 | Human Rights organisations | C | External | Needs: Social equity & ethical infrastructure deployment.Requirements: Fair practices, clear community impact statements. | Advocate | M | Inform | Supply transparent social impact and project progress briefs. | 2026-11-23 | On demand
18 | The project team | A | Internal | Needs: Resource allocation & cross-functional collaboration.Requirements: Transparent communication, role alignment. | Advocate | H | Involve | Conduct daily stand-ups and active progress sharing. | 2026-06-01 | Daily
19 | Public Media | C | External | Needs: Public interest stories & accurate information.Requirements: Transparent press releases, strategic alignment. | Neutral | L | Manage | Issue official corporate press releases regarding major milestones. | 2026-08-24 | Quarterly
20 | Local government officials | B | External | Needs: Municipal alignment & regional funding approval.Requirements: Zoning compliance, public welfare preservation. | Supporter | M | Inform | Deliver high-level executive briefs on project milestones. | 2026-06-01 | Quarterly
Note on B2: Individual or organisation.
Note on C2: Stakeholders' relationship to the project: A: High power - high interest B: High power - low interest C: Low power - high interest D: Low power - low interest
Note on D2: Internal or external
Note on E2: Main reason for stake. Do not forget that here a two-way relationship has to be described, i.e. how stakeholders can impact the project and how project can impact the stakeholders.
Note on F2: Stakeholder view: Very positive: Advocate Positive: Supporter Neutral: Neutral Negative: Critic Very negative: Very critic
Note on G2: L = Low M = Medium H = High
Note on H2: Strategy for management approach: Watch Inform Dialogue Support Involve Influence Manage
Note on I2: explain the strategy for management and choose communication channels
Note on J2: Latest date implementation should be carried out
Note on K2: labas: Describe the frequency of the communication

## Defs
Category: | View: | Priority: | Strategy: | Status: | Type:
A | Advocate | L | Watch | Registered | Internal
B | Supporter | M | Inform | Ongoing | External
C | Neutral | H | Dialogue | Finished
D | Critic |  | Support | Postponed
| Very critic |  | Involve
Influence
Manage

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only