Identify vandalism-prone infrastructure areas
 Highlight locations and assets most frequently affected by vandalism.

Propose alternative low-cost materials
 Suggest materials with lower resale value that could reduce vandalism incentives.

Evaluate potential impact on vandalism
 Assess how changing materials could influence vandalism rates and behavior.

Assess economic impact
 Estimate potential cost savings in repair and replacement due to vandalism.

Analyze risks and limitations
 Identify possible drawbacks (e.g., reduced durability, higher failure rates).

Develop implementation recommendations
 Outline how the organization could gradually introduce cheaper materials (e.g., pilot areas).

Suggest monitoring approach
 Recommend how to track vandalism incidents and cost changes after implementation.

Provide final justification
 Summarize why this solution is beneficial specifically for reducing vandalism impact.

1 Project Management

1.1 Project Charter & Scope Statement: Defining boundaries and success metrics.

1.2 Schedule & Budget Baseline: Establishing the Gantt chart and cost controls.

1.3 Risk Management Plan: Identifying technical and operational risks.

1.4 Stakeholder Communications: Keeping in contact with rand water.

2 Research and Requirements

2.1 Vandalism Report: Analysis of damage data from the water provider.

2.2 Material Benchmarking: Comparative study of potential materials.

2.3 Estimate potential cost savings in repair and replacement due to vandalism.

2.4 Compliance & Regulatory Analysis: Ensuring correct standards.

3 Engineering and Design

3.1 Conceptual CAD Models: Initial 3D designs.

3.2 Digital Analysis Report: Digital testing.

3.3 Hydraulic Modeling: Ensuring the internal geometry doesn't cause cavitation or pressure drops.

3.4 Final Technical Drawings: "Ready-for-Manufacture" blueprints.

4 Testing and Quality Assurance

4.1 Hydrostatic Testing: Standard pressure testing to ensure it functions.

4.2 Attack Testing: Executing the "Vandalism Scenarios" in a lab environment.

4.3 Failure Analysis: Documenting exactly how the part fails under extreme stress or vandalism tests.

5 Project Closure and Handover

5.1 Final Prototype Delivery: Handing over the blueprints to the stakeholders.

5.2 Technical Documentation Package: Providing the testing results.

5.3 Lessons Learned & Closeout Report: Archiving project data for the presentation.