## Project budget.
Project Budget | [9 empty] | © 2019 Vertex42 LLC
| Project Name: |  | Using cheapier materials (to deal with vandalism) |  |  |  | [42] | Budget (without 10% risk budget) | Budget (with 10% risk budget)
| Start Date: |  | 2026-06-01 |  |  |  |  | 29715 | 32686.5
| End Date: |  | 2026-12-01
| Labor |  | Materials |  | Fixed Costs
Tasks | Hrs | Rate | Units | €/Unit | Material | Travel | Other | Budget | Comments
Phase One: Initiation | [7 empty] | 2713.2
1.1 Project Charter & Scope Analysis | 40 | 13.52 | [5 empty] | 540.8 | 1 Project Manager is working on this task
1.2 Schedule & Budget Baseline | 40 | 13.52 | [5 empty] | 540.8 | 1 Project Manager is working on this task
1.3 Stakeholder Communication Plan | 40 | 13.52 |  |  |  | 300 | 250 | 1090.8 | 1 Project Manager is working on this task; Travel: a lot of local trips; Other: printing documents (up to 500 pages at R10.8 rate)
1.4 Risk Management Plan | 40 | 13.52 | [5 empty] | 540.8 | 1 Project Manager is working on this task
Phase Two: Planning & Procurement | [7 empty] | 8334.2
2.1 Vandalism Report | 80 | 8.91 |  |  |  | 150 | 250 | 1112.8 | 1 person from Operations Department; Travel: travelling to sites. Other: printing documents (up to 500 pages at R10.8 rate).
2.2 Material Benchmarking | 80 | 31.88 |  |  | 1725 |  |  | 4275.4 | 2 Materials Scientists; Material: samples for testing & benchmarking.
2.3 Cost Savings Estimation | 40 | 13.52 | [5 empty] | 540.8 | 1 Project Manager is working on this task
2.4 Compliance & Regulatory Analysis | 40 | 27.42 |  |  |  |  | 250 | 1346.8 | 1 Senior Mechanical Engineer; Other: printing documents (up to 500 pages at R10.8 rate).
2.5 End-to-end procurement and contracting process | 120 | 8.82 | [5 empty] | 1058.4 | 1 Supply Chain Manager
2.5.1 Procurement Preparation | 40 | 8.82 | [5 empty] | 352.8 | 1 Supply Chain Manager
2.5.2 Supplier tendering and evaluation | 40 | 8.82 | [5 empty] | 352.8 | 1 Supply Chain Manager
2.5.3 Decision, Legal procedures & Document signing | 40 | 8.82 | [5 empty] | 352.8 | 1 Supply Chain Manager
Phase Three: Execution | [7 empty] | 10965.6
3.1 Conceptual CAD Models | 80 | 16.75 |  |  | 4152 |  |  | 5492 | 1 Mechanical Engineer; Material: Solid Works yearly subscription.
3.1.1. Design the device | 50 | 16.75 | [5 empty] | 837.5 | 1 Mechanical Engineer
3.1.2. Create the CAD model | 30 | 16.75 | [5 empty] | 502.5 | 1 Mechanical Engineer
3.2 Digital Testing | 80 | 16.75 | [5 empty] | 1340 | 1 Mechanical Engineer
3.2.1. Verify structural strength | 40 | 16.75 | [5 empty] | 670 | 1 Mechanical Engineer
3.2.2. Verify proper fluid flow | 40 | 16.75 | [5 empty] | 670 | 1 Mechanical Engineer
3.3 Prototype Verification | 80 | 16.75 |  |  | 600 |  |  | 1940 | 1 Mechanical Engineer; Material: materials for prototype testing, based on industry standard costs.
3.4 Final Technical Drawings | 80 | 27.42 | [5 empty] | 2193.6 | 1 Senior Mechanical Engineer
Phase Four: Control | [7 empty] | 3972
4.1 Testing Under Real-Life Conditions | 120 | 33.5 | [5 empty] | 1986 | 2 Mechanical Engineers
4.1.1.Controlled enviroment testing | 60 | 33.5 | [5 empty] | 2010 | 2 Mechanical Engineers
4.1.2.In location testing | 60 | 33.5 | [5 empty] | 2010 | 2 Mechanical Engineers
4.2 Monitoring Vandalism of New Product | 120 | 16.55 | [5 empty] | 1986 | 1 Quality Assurance Engineer
Phase Five: Closeout | [7 empty] | 3730
5.1 Final Prototype Delivery | 40 | 27.42 |  |  |  | 400 |  | 1496.8 | 1 Senior Mechanical Engineer; travel: local trips
5.2 Technical Documentation Package | 60 | 27.42 |  |  |  |  | 250 | 1895.2 | 1 Senior Mechanical Engineer; Other: printing documents (up to 500 pages at R10.8 rate)
5.3 Lessons Learned | 25 | 13.52 | [5 empty] | 338 | 1 Project Manager is working on this task
Note on B7: Employees and machinery which need time (hours/days) to perform
Note on D7: Materials (such as bricks, oil, concrete, etc.) which do not depend on time.
Note on F7: A fixed cost defines a single price for the service or product regardless of how much time and expense your company incurs.
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Yearly salary: https://www.jobted.co.za/salary/project-manager Hourly salary converter: https://www.hiresava.com/south-african-salary-calculator
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Yearly salary: https://www.jobted.co.za/salary/project-manager Hourly salary converter: https://www.hiresava.com/south-african-salary-calculator
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Yearly salary: https://www.jobted.co.za/salary/project-manager Hourly salary converter: https://www.hiresava.com/south-african-salary-calculator
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.gov.za/news/media-statements/minister-gwede-mantashe-announces-adjustment-fuel-prices-effective-6-may-2026 Reply: https://sandtoncity.com/parking/ https://www.fcmtravel.com/en-za/resources/insights/business-travel-spend-south-africa-how-does-it-stack-2024
Note on H12: https://alloutprint.co.za/product/copying-and-printing/ https://www.printandcopy.co.za/printing-2/flyer-price-list/
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Yearly salary: https://www.jobted.co.za/salary/project-manager Hourly salary converter: https://www.hiresava.com/south-african-salary-calculator
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://za.indeed.com/career/operation-specialist/salaries
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.gov.za/news/media-statements/minister-gwede-mantashe-announces-adjustment-fuel-prices-effective-6-may-2026
Note on H15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.printandcopy.co.za/printing-2/flyer-price-list/
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://worldsalaries.com/average-materials-scientist-salary-in-south-africa/
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.tradewheel.com/p/hdpe-resin-virginrecycled-hdpe-granules-hdpe-181799/ Reply: https://www.tradewheel.com/p/polypropylene-granules-virgin-pp-plastic-raw-181123/
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.jobted.co.za/salary/project-manager
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on H18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.printandcopy.co.za/printing-2/flyer-price-list/
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://za.indeed.com/career/supply-chain-manager/salaries?from=top_sb
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on F24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.solidworks.com/how-to-buy/solidworks-design-plans-pricing
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Eilinis inžinierius. Tiek pat kiek 3.3 ir 3.1
Note on C26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Eilinis inžinierius. Tiek pat kiek 3.3 ir 3.1
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Eilinis inžinierius. Tiek pat kiek 3.3 ir 3.1
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Eilinis inžinierius. Tiek pat kiek 3.3 ir 3.1
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on F30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://3dprintdesk.com/blog/how-to-calculate-3d-print-costs
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Eilinis inžinierius. Tiek pat kiek 3.3 ir 3.1 Reply: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Eilinis inžinierius. Tiek pat kiek 3.3 ir 3.1
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Eilinis inžinierius. Tiek pat kiek 3.3 ir 3.1
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://za.indeed.com/career/quality-assurance-engineer/salaries (Žiūrėta 2026 05 15)
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on G38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.gov.za/news/media-statements/minister-gwede-mantashe-announces-adjustment-fuel-prices-effective-6-may-2026
Note on C39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ourpower.co.za/jobs/salary/mechanical-engineer
Note on H39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.printandcopy.co.za/printing-2/flyer-price-list/
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.jobted.co.za/salary/project-manager

## Help
Template Help
Visit the Project Budget Template Page >
About This Template
This version of the project budget template was designed with a new look and it provides multiple columns for fixed costs. Also, instead of using the Labor, Materials, and Fixed Costs columns to calculate the Budgeted amount, these columns are used to calculate the Actual amount.
Entering Budget and Actual Amounts
In this worksheet, the Actual amount is calculated from the Labor, Materials, and Fixed Costs columns. This means that you manually enter the Budget value and you use the Labor, Materials, and Fixed Costs columns to enter actual spent amounts.
When Adding New Rows
The Phase/Category Title rows contain SUBTOTAL(9,...) formulas in the Budget and Actual columns that should be verified for accuracy after inserting new rows. Check these formulas to ensure that they reference the correct range of cells.
Note: The SUBTOTAL(9,…) function is the same as the SUM(…) function except that using SUBTOTAL() ignores cells containing other SUBTOTAL() formulas. This allows the grand-total at the top to sum all budget values while ignoring the subtotals.
Cell containing "#####"
If you see "#####" in a cell, it means you need to widen the column to see the value, or reduce the font size for that cell.

## ©
Project Budget Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-budget.html
© 2019 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.